## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a founder, I want to submit a startup idea through the frontend so that the system can begin the validation workflow. | MUST HAVE | None | Lahari | Done
Sprint 1 | Sprint 1 | US-02 | As a founder, I want the system to define a clear input contract so that startup ideas and research parameters are passed consistently between components. | MUST HAVE | US-01 | Abhipsha | Done
Sprint 1 | Sprint 1 | US-03 | As a founder, I want my startup idea converted into targeted search queries so that the web search focuses on competitors, market information, trends and related evidence. | MUST HAVE | US-01 | Shreya | Done
Sprint 1 | Sprint 1 | US-04 | As a founder, I want live web information retrieved through the search service so that validation is based on current external evidence rather than only LLM knowledge. | MUST HAVE | US-03 | Abhipsha | Done
Sprint 1 | Sprint 1 | US-05 | As a founder, I want search failures, empty results and malformed responses handled gracefully so that one failure does not crash the workflow. | SHOULD HAVE | US-04 | Neha | Done
Sprint 1 | Sprint 1 | US-06 | As a founder, I want search results cleaned and returned in a standardized structure so that downstream agents can consume them reliably. | MUST HAVE | US-04, US-05 | Abhipsha | Done
Sprint 1 | Sprint 1 | US-07 | As a project team, we want architecture and workflow diagrams showing the Web Search Agent, Query Strategist, Tavily service, result processing and downstream handoff. | SHOULD HAVE | US-02–US-06 | Lahari | Done
Sprint 2 | Sprint 2 | US-08 | As a founder, I want market analysis of market size, trends and demand so that I can understand the opportunity around my idea. | MUST HAVE | US-06 | Shreya | Done
Sprint 2 | Sprint 2 | US-09 | As a founder, I want customer analysis covering target segments, personas, pain points and needs so that the product is evaluated against identifiable users. | MUST HAVE | US-06 | Lahari | Done
Sprint 2 | Sprint 2 | US-10 | As a founder, I want competitor analysis covering competitors, features, pricing and positioning so that I can understand the competitive landscape. | MUST HAVE | US-06 | Neha | Done
Sprint 2 | Sprint 2 | US-11 | As a founder, I want a comparison layer that combines market, customer and competitor findings so that I receive a coherent validation rather than isolated analyses. | MUST HAVE | US-08–US-10 | Abhipsha | Done
Sprint 2 | Sprint 2 | US-12 | As a founder, I want agents to exchange structured information through a coordinated workflow so that each agent can focus on one responsibility without duplicating web research. | MUST HAVE | US-08–US-11 | Shreya | Done
Sprint 2 | Sprint 2 | US-13 | As a founder, I want robust JSON validation and fallback handling so that malformed LLM outputs or API failures are contained without crashing the system. | SHOULD HAVE | US-08–US-12 | Neha | Done
Sprint 2 | Sprint 2 | US-14 | As a project team, we want detailed UML, architecture and use-case documentation that matches the implemented workflow. | SHOULD HAVE | US-11, US-12 | Lahari | Done
Sprint 2 | Sprint 2 | US-15 | As a founder, I want the integrated validation workflow deployed so that the application can be tested end-to-end outside the development environment. | MUST HAVE | US-11–US-14 | Shreya | Done
Sprint 3 | Sprint 3 | US-16 | As a founder, I want architectural planning and design for the newly introduced strategic agents (SWOT, Risk, MVP, GTM, Advisory) so that their implementation and cross-agent communication follow a structured approach. | MUST HAVE | US-11 | Abhipsha | Done
Sprint 3 | Sprint 3 | US-17 | As a founder, I want SWOT analysis derived from existing market, customer and competitor evidence so that the validation includes strategic strengths, weaknesses, opportunities and threats. | MUST HAVE | US-08–US-11 | Abhipsha | Done
Sprint 3 | Sprint 3 | US-18 | As a founder, I want dedicated risk analysis covering market, competitive, customer/adoption, feasibility and business risks so that recommendations account for uncertainty. | MUST HAVE | US-08–US-11 | Neha | Done
Sprint 3 | Sprint 3 | US-19 | As a founder, I want MVP features prioritized using MoSCoW so that I know which features are essential for an initial launch and which can be deferred. | SHOULD HAVE | US-11, US-17, US-18 | Lahari | Done
Sprint 3 | Sprint 3 | US-20 | As a founder, I want go-to-market recommendations covering positioning, channels and early customer acquisition so that validation leads toward an actionable launch strategy. | SHOULD HAVE | US-11, US-19 | Shreya | Done
Sprint 3 | Sprint 3 | US-21 | As a founder, I want a conversational AI advisor (Vera Chatbot) grounded in my startup research so that I can ask follow-up questions instead of relying on static validation output. | MUST HAVE | US-11, US-17–US-20 | Shreya | Done
Sprint 3 | Sprint 3 | US-22 | As a founder, I want a startup validation scorecard so that I receive an overall viability rating with category breakdowns. | MUST HAVE | US-08–US-11 | Shreya | Done
Sprint 3 | Sprint 3 | US-23 | As a founder, I want a frontend dashboard with progress tracking, report visualization, workspace management, history and PDF export so that I can manage and share validation results. | MUST HAVE | US-15, US-20 | Shreya | Done
Sprint 3 | Sprint 3 | US-24 | As a founder, I want authentication, database integration and production deployment on Render so that the platform is secure and accessible. | MUST HAVE | US-23 | Shreya | Done
Sprint 3 | Sprint 3 | US-25 | As a project team, we want final end-to-end testing, documentation, licensing and deployment checks so that the project is ready for evaluation. | MUST HAVE | US-17–US-24 | Shreya / Neha | Done
Sprint 3 | Sprint 3 | US-26 | As a founder, I want all analytical and strategic agents orchestrated through a unified mesh so that validation runs as a single coordinated pipeline rather than isolated agent calls. | MUST HAVE | US-12, US-17–US-22 | Shreya | Done
Sprint 3 | Sprint 3 | US-27 | As a founder, I want the platform to be performance-hardened with caching, rate limiting, error boundaries and async task management so that the system is stable under production load. | MUST HAVE | US-24, US-26 | Shreya | Done
Sprint 3 | Sprint 3 | US-28 | As a founder, I want workspace management with project history, version comparison and asset library so that I can organize and track multiple validation sessions. | MUST HAVE | US-23 | Shreya | Done
Sprint 3 | Sprint 3 | US-29 | As a founder, I want automated report generation with investor-grade PDF and presentation export so that I can share validation results with stakeholders. | MUST HAVE | US-23, US-26 | Shreya | Done
Sprint 1 | Sprint 1 | US-30 | As a founder, I want a Query Strategist that decomposes my startup idea into categorized search queries covering market, competitor, customer and trend dimensions so that web research is targeted and comprehensive. | MUST HAVE | US-01 | Shreya | Done
Sprint 3 | Sprint 3 | US-31 | As a founder, I want the complete VentureLens platform tested end-to-end across all agents, APIs, authentication, database, frontend and deployment so that the system is production-ready and stable. | MUST HAVE | US-26–US-29 | Shreya | Done
Sprint 3 | Sprint 3 | US-32 | As a founder, I want a What-If Simulator that lets me change assumptions and see recalculated impact on market potential, customer fit, competitive risk and overall viability so that I can explore alternative scenarios. (Concept proposed by Abhipsha; designed, developed and deployed by Shreya.) | SHOULD HAVE | US-22, US-26 | Shreya | Done
Sprint 3 | Sprint 3 | US-33 | As a project team, we want collaborative UI/UX testing covering usability, navigation, workflow validation and dashboard review so that the platform meets user experience standards. | SHOULD HAVE | US-23 | Abhipsha / Neha / Lahari | Done
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 361 | 291.8 | 222.4 | 153.1 | 83.9 | 66 | 47.8 | 30.9 | 14.4 | 7.2 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-01 | T-01 | Define startup-idea submission flow and frontend input expectations | 2026-07-01 | 2026-07-02 | Lahari | Design | Done | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-02 | T-02 | Define input contract and output schema for the Web Search Agent | 2026-07-02 | 2026-07-04 | Abhipsha | Design | Done | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-03 | T-03 | Design query decomposition prompt and targeted query categories | 2026-07-03 | 2026-07-06 | Shreya | Prompt Engineering | Done | 7 | 5.2 | 3.5 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-04 | T-04 | Integrate Tavily search service and test live search_web() | 2026-07-04 | 2026-07-08 | Abhipsha | Coding | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-05 | T-05 | Document API failures, empty results, rate limits and niche-query handling | 2026-07-05 | 2026-07-09 | Neha | Analysis / Testing | Done | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-06 | T-06 | Implement result processing and structured JSON handoff | 2026-07-07 | 2026-07-10 | Abhipsha | Coding | Done | 7 | 5.2 | 3.5 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-07 | T-07 | Create Web Search Agent architecture and MAS workflow diagrams | 2026-07-08 | 2026-07-13 | Lahari | Documentation | Done | 7 | 5.2 | 3.5 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-08 | T-08 | Implement Market Analysis Agent using structured research context | 2026-07-15 | 2026-07-21 | Shreya | Coding | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-09 | T-09 | Implement Customer Analysis Agent for segments, personas and pain points | 2026-07-16 | 2026-07-23 | Lahari | Coding | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-10 | T-10 | Implement Competitor Agent and competitive-gap analysis | 2026-07-17 | 2026-07-25 | Neha | Coding | Done | 9 | 6.8 | 4.5 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-11 | T-11 | Implement Comparison Agent and structured synthesis outputs | 2026-07-18 | 2026-07-28 | Abhipsha | Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-12 | T-12 | Establish A2A/shared-context coordination between analytical agents | 2026-07-21 | 2026-07-29 | Shreya | Integration | Done | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-13 | T-13 | Add JSON validation, repair, fallback and edge-case handling | 2026-07-22 | 2026-07-30 | Neha | Coding / Testing | Done | 7 | 5.2 | 3.5 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-14 | T-14 | Update architecture and use-case diagrams to match implementation | 2026-07-24 | 2026-08-02 | Lahari | Documentation | Done | 7 | 5.2 | 3.5 | 1.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-15 | T-15 | Complete backend integration and production deployment workflow | 2026-07-28 | 2026-08-04 | Shreya | Integration / Deploy | Done | 12 | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-16 | T-16 | Architectural planning and design for Sprint 3 agents (SWOT, Risk, MVP, GTM, Advisory) including cross-agent workflows | 2026-08-11 | 2026-08-13 | Abhipsha | Design | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-17 | T-17 | Implement SWOT Agent using Market, Customer and Competitor evidence | 2026-08-11 | 2026-08-18 | Abhipsha | Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-18 | T-18 | Implement Risk Agent with structured risk categories and mitigation | 2026-08-12 | 2026-08-19 | Neha | Coding | Done | 9 | 6.8 | 4.5 | 2.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-19 | T-19 | Implement MVP Recommendation Agent with MoSCoW prioritization | 2026-08-14 | 2026-08-20 | Lahari | Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-20 | T-20 | Implement GTM Agent and Roadmap Agent strategy outputs | 2026-08-15 | 2026-08-21 | Shreya | Coding | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-21 | T-21 | Implement Vera AI Chatbot with streaming, memory and multi-mode personas | 2026-08-16 | 2026-08-22 | Shreya | Coding | Done | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-22 | T-22 | Implement Startup Scorecard Agent with category breakdowns | 2026-08-18 | 2026-08-23 | Shreya | Coding | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-23 | T-23 | Build frontend dashboard, workspace, history, PDF export and report UI | 2026-08-19 | 2026-08-25 | Shreya | Coding | Done | 12 | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | 0 | 0 | 0 | 0
US-24 | T-24 | Implement JWT auth, database models, Render deployment and CI/CD | 2026-08-22 | 2026-08-27 | Shreya | Integration / Deploy | Done | 12 | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | 0 | 0 | 0 | 0
US-25 | T-25 | E2E testing, documentation, license checks and final validation | 2026-08-25 | 2026-08-29 | Shreya / Neha | Testing / Docs | Done | 10 | 8.8 | 7.5 | 6.2 | 5 | 3.8 | 2.5 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-26 | T-26 | Build orchestrator mesh with parallel agent execution and shared context | 2026-08-18 | 2026-08-25 | Shreya | Integration | Done | 12 | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | 0 | 0 | 0 | 0
US-26 | T-27 | Implement agent error boundaries, guardrails and response validation | 2026-08-20 | 2026-08-26 | Shreya | Integration | Done | 10 | 8.8 | 7.5 | 6.2 | 5 | 3.8 | 2.5 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-27 | T-28 | Add semantic search caching, cache stampede protection and rate limiting | 2026-08-24 | 2026-08-27 | Shreya | Performance | Done | 10 | 8.8 | 7.5 | 6.2 | 5 | 3.8 | 2.5 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-27 | T-29 | Production stabilization: async locks, telemetry, background task hardening | 2026-08-26 | 2026-08-29 | Shreya | Deployment | Done | 12 | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | 0 | 0 | 0 | 0
US-28 | T-30 | Implement workspace routes, project CRUD and session management | 2026-08-19 | 2026-08-24 | Shreya | Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-28 | T-31 | Build history tracking, version comparison and asset library APIs | 2026-08-21 | 2026-08-25 | Shreya | Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-29 | T-32 | Implement report generation service with section builders and PDF export | 2026-08-22 | 2026-08-26 | Shreya | Coding | Done | 12 | 9 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-29 | T-33 | Integrate export aggregator and presentation exporter pipeline | 2026-08-23 | 2026-08-27 | Shreya | Integration | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-30 | T-34 | Implement query strategist with categorized prompt decomposition and rules engine | 2026-07-03 | 2026-07-08 | Shreya | Coding | Done | 10 | 7.5 | 5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-31 | T-35 | Execute cross-agent integration testing and fix orchestration race conditions | 2026-08-25 | 2026-08-28 | Shreya | Testing | Done | 12 | 10.8 | 9.6 | 8.4 | 7.2 | 6 | 4.8 | 3.6 | 2.4 | 1.2 | 0 | 0 | 0 | 0 | 0
US-31 | T-36 | Final deployment validation, environment configuration and release stabilization | 2026-08-27 | 2026-08-29 | Shreya | Deployment | Done | 10 | 8.8 | 7.5 | 6.2 | 5 | 3.8 | 2.5 | 1.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-32 | T-37 | Design, implement and integrate What-If Simulator with LLM-powered scenario evaluation | 2026-08-20 | 2026-08-26 | Shreya | Coding / Integration | Done | 12 | 10.5 | 9 | 7.5 | 6 | 4.5 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-33 | T-38 | Collaborative UI/UX testing: usability, navigation, workflow and dashboard review | 2026-08-22 | 2026-08-27 | Abhipsha / Neha / Lahari | Testing | Done | 8 | 6 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-25 | T-39 | Cross-agent output verification, edge-case regression testing and release validation | 2026-08-24 | 2026-08-28 | Neha | Testing | Done | 8 | 6.7 | 5.3 | 4 | 2.7 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | 3 | Tavily API rate limits blocking automated tests | Mocked responses for dev environment; rotated API keys
Sprint 1 | 7 | Query decomposition returning generic results for niche ideas | Shreya refined prompt categories; Neha added edge-case fallbacks
Sprint 1 | 10 | Architecture diagrams not matching updated code flow | Lahari reviewed implementation before finalizing MAS diagrams
Sprint 2 | 3 | LLM hallucinations in Customer Agent persona generation | Refined prompt with stricter Pydantic output constraints
Sprint 2 | 5 | Competitor Agent returning inconsistent competitor counts across similar industries | Neha added deduplication logic and normalized competitor name matching in competitor_agent.py
Sprint 2 | 7 | Competitor Agent taking too long on broad industries | Implemented parallel async calls; Neha added timeout fallbacks
Sprint 2 | 9 | Comparison Agent I/O schema mismatch with upstream agents | Abhipsha unified Pydantic contracts across all analytical agents
Sprint 2 | 12 | Frontend/backend integration issues during deployment | Shreya resolved credential and API routing configuration
Sprint 3 | 1 | Market Agent TAM/SAM/SOM estimates producing unrealistic numbers for niche markets | Shreya refined market sizing prompts and added validation bounds in market_agent.py
Sprint 3 | 2 | Risk Agent failing on obscure startup niches | Neha added fallback risk categories and default mitigation logic
Sprint 3 | 3 | Risk assessment severity scores inconsistent between niche and broad market ideas | Neha standardized risk category weighting and added calibration bounds in risk_agent.py
Sprint 3 | 4 | SWOT generation producing inconsistent evidence references | Abhipsha added cross-validation against Market/Competitor outputs
Sprint 3 | 5 | Vera Chatbot prompt injection and context overflow risks | Shreya added strict rate limiting, input sanitization and context truncation
Sprint 3 | 6 | Customer Analysis segments not rendering correctly in dashboard visualization | Lahari validated customer persona data flow and coordinated frontend fix with Shreya
Sprint 3 | 7 | PDF Export crashing on missing nested list data | Shreya added default empty strings and None checks before concatenation
Sprint 3 | 8 | What-If Simulator LLM responses returning markdown-wrapped JSON instead of raw JSON | Shreya added regex cleanup and structured JSON parsing with fallback in simulator_routes.py
Sprint 3 | 9 | SQLite disk I/O race conditions during parallel validation | Shreya switched to async lock mechanism for background task management
Sprint 3 | 10 | Cross-agent output schemas diverging after individual agent updates | Neha ran regression tests across all agent outputs; Shreya fixed contract mismatches in orchestrator
Sprint 3 | 11 | Orchestrator mesh race condition causing duplicate agent runs | Shreya implemented mutex locks and deduplication in the task queue
Sprint 3 | 12 | Dashboard usability issues identified during collaborative UI/UX review | Abhipsha, Neha and Lahari conducted usability testing; Shreya applied navigation and layout fixes
Sprint 3 | 13 | Render deployment memory limits exceeded during scoring | Shreya optimized model loading and added cache stampede protection
Sprint 3 | 14 | MVP recommendation priorities not aligning with final MoSCoW classification | Lahari refined MVP feature ranking; Neha verified edge-case coverage for release readiness

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2026-07-01 | 2026-07-13 | Abhipsha | Validating I/O assumptions with downstream agents earlier | Leaving interface decisions implicit | Defining explicit schemas and field types | Maintained versioned I/O contracts before integration
2 | 1 | 2026-07-01 | 2026-07-13 | Shreya | Sharing query-strategy examples alongside prompt design | Treating query generation as a single generic search | Decomposing startup ideas into targeted research areas | Kept query categories explicit and testable
3 | 1 | 2026-07-01 | 2026-07-13 | Neha | Edge-case analysis while features are being designed | Waiting until integration to consider failure modes | Focusing on graceful degradation | Attached failure scenarios to each agent contract
4 | 1 | 2026-07-01 | 2026-07-13 | Lahari | Validating diagrams against the actual code flow | Treating the diagram as a one-time artifact | Maintaining architecture documentation | Reviewed diagrams whenever an interface or workflow changed
5 | 2 | 2026-07-14 | 2026-08-04 | Abhipsha | Integration checks earlier when adding a new agent | Assuming correct standalone output guarantees E2E compatibility | Structured outputs and synthesis design | Used Comparison Agent contract as an integration checkpoint
6 | 2 | 2026-07-14 | 2026-08-04 | Shreya | Maintaining a single view of integration status; validating Market Agent TAM/SAM estimates against external benchmarks | Allowing branch changes to remain unsynchronized | Orchestration and research-layer ownership | Tracked branch/PR readiness before merging; refined market sizing prompts for accuracy
7 | 2 | 2026-07-14 | 2026-08-04 | Neha | Regression testing after every agent-interface change | Postponing robustness checks | Structured error handling | Maintained reusable edge-case tests
8 | 2 | 2026-07-14 | 2026-08-04 | Lahari | Checking demo flow before the final presentation period | Relying on last-minute diagram/demo preparation | Supporting architecture and documentation | Kept current architecture and use-case diagrams in docs
9 | 3 | 2026-08-11 | 2026-08-29 | Abhipsha | Separating implemented features from future proposals in Agile records | Marking future architecture as completed implementation | Using evaluator feedback to refine product direction | Recorded SWOT implementation separately from planned extensions
10 | 3 | 2026-08-11 | 2026-08-29 | Shreya | Running integration smoke tests after each agent merge; coordinating cross-agent data flow and validating end-to-end workflow before each deployment | Treating individual agent completion as equivalent to full platform integration | Modular orchestration, cross-agent validation, research-layer reuse and centralized release coordination | Delivered complete platform: orchestrator mesh, auth, DB, APIs, dashboard, reports, chatbot, What-If simulator and Render deployment
11 | 3 | 2026-08-11 | 2026-08-29 | Neha | Edge-case test design alongside Risk implementation; cross-agent regression testing during integration phase | Waiting for final E2E integration to validate robustness | Failure analysis and validation | Maintained risk and LLM failure checklists; verified cross-agent output consistency before release
12 | 3 | 2026-08-11 | 2026-08-29 | Lahari | Validating MVP recommendations against actual project constraints; verifying customer analysis visualizations in dashboard | Assigning every proposed feature the same priority | Architecture/documentation support, diagram review and presentation preparation | Used MoSCoW to distinguish launch scope from future ideas; validated customer segment rendering and participated in UI/UX review
13 | 3 | 2026-08-11 | 2026-08-29 | Shreya | Automated cross-agent integration tests before each deployment; implemented What-If Simulator from Abhipsha concept through to production deployment | Deferring workspace, report and simulator integration until after all agents are individually complete | Centralized orchestration ownership, end-to-end platform coordination and structured release management | Completed structured release: auth, DB, agents, APIs, frontend, export, simulator and deployment verified; project delivered successfully
14 | 3 | 2026-08-11 | 2026-08-29 | Abhipsha | Proposing feature concepts (What-If Simulator) and defining requirements alongside agent implementation | Limiting contributions to only assigned agent work | Structured I/O design, SWOT synthesis and creative feature ideation | What-If Simulator concept adopted by team and implemented into the final platform by Shreya; SWOT Agent delivered successfully
15 | 3 | 2026-08-11 | 2026-08-29 | Abhipsha / Neha / Lahari | Performing collaborative UI/UX testing to validate usability and workflow consistency | Skipping frontend review before deployment | Supporting overall product quality through testing and feedback | Completed usability review, navigation testing, dashboard validation and workflow verification across the platform
16 | 3 | 2026-08-11 | 2026-08-29 | Neha | Running cross-agent regression tests and output schema verification before each release candidate | Delaying validation checks until after full integration is complete | Edge-case analysis, failure scenario coverage and structured error handling | Validated all agent outputs for consistency; contributed to final release verification alongside Shreya